## Sheet1
Investment Name | Site Name | Build Period | Count | Site Postcode | Legal Review Status | Risk Rating | Risk Comments | Site Expected or Actual Start Date (for Multi-Site Builds this reflects the earliest date) | Grant Amount | Grant Capital | Grant Revenue | Disbursed Amount | Disbursed Capital | Disbursed Revenue | Proportion of Capital Disbursed | Postcode | Latitude | Longitude | Region
YIF - Pompey in the Community - 2022 |  | 16 | 1 | PO3 6LA | Completed | Green | Grant reapproved at the Aug. 23 GC - revenue grant increased to support capacity issues. Phase 1 completion works progressing. | 01/09/2021 | 893100 | 744250 | 148850 | 818100 | 743100 | 75000 | 0.99845 | PO3 6LA | 50.8138 | -1.0593 | South East
YIF - The Seagull Lowestoft Community Interest Company - 2022 |  | 76 | 1 | NR33 0JH | Completed | Green | 27 weeks start on site to completion | 01/07/2022 | 526890 | 438250 | 88640 | 451054.1 | 412619.1 | 38435 | 0.94152 | NR33 0JH | 52.4571 | 1.7354 | East of England
YIF - NSC CARE LTD - 2022 |  | 20 | 1 | L11 0BS | Completed | Green | Complete | 03/01/2023 | 717276 | 597776 | 119500 | 604676 | 597776 | 6900 | 1 | L11 0BS | 53.4559 | -2.8986 | North West
YIF - Nottingham Mencap - 2022 |  | 40 | 1 | NG3 2ET | Completed | Green | 40 weeks start on site to completion | 09/01/2023 | 445400 | 395800 | 49600 | 392780 | 370780 | 22000 | 0.93679 | NG3 2ET | 52.9561 | -1.1336 | East Midlands
YIF - NSC HOME FARM LTD - 2022 |  | 48 | 1 | L12 0HB | In Progress | Green | 16 week start on site to completion. Update 30/1/24 Still waiting for lease to be resolved. Works could complete quickly once agreed. Senior council official visiting Farm early in new year with aim of resolving lease issues but been delayed due to | 01/02/2023 | 330067 | 330067 | 0 | 150000 | 150000 | 0 | 0.45445 | L12 0HB | 53.4426 | -2.8918 | North West
YIF - The Vulcan Centre - 2022/3 |  | 41 | 1 | HU3 3PF | Completed | Green | 29 weeks start on site to completion | 01/02/2023 | 1027591 | 871191 | 156400 | 879159.98 | 856120.3 | 23040 | 0.9827 | HU3 3PF | 53.7419 | -0.37009 | Yorkshire and The Humber
YIF - Liberdade Community Development Trust - 2022 |  | 26 | 1 | NE3 3HD | Completed | Green | 26 weeks start on site to completion | 06/02/2023 | 1689989 | 1498429 | 191560 | 1689989 | 1498429 | 191560 | 1 | NE3 3HD | 55.0111 | -1.6304 | North East
YIF - Houghton Regis Town Council - 2022/3 |  | 26 | 1 | LU5 5JB | Completed | Green | 30 week start on site to completion | 23/03/2023 | 771902 | 699842 | 72060 | 714254 | 699842 | 14412 | 1 | LU5 5JB | 51.9106 | -0.52055 | East of England
YIF - Lincoln City Foundation - 2022 |  | 38 | 1 | LN5 8LD | In Progress | Green | Project has started on site YIF funding internal refurbishment No More disbursements until Lease sorted | 22/05/2023 | 800000 | 625000 | 175000 | 645475 | 576994 | 68481 | 0.92319 | LN5 8LD | 53.2182 | -0.54006 | East Midlands
YIF - Marine Society and Sea Cadets - 2022 |  | 56 | 1 | B16 9EE | Completed | Green | The applicant’s 52-week assessment is considered reasonable - Project on Site -Forecast for completion 26/07/2024 - Record need updated to reflect accuracy around this. Building Control concern appears in F21 & Ridge Report | 26/06/2023 | 2100000 | 2100000 | 0 | 1091813.54 | 1091813.54 | 0 | 0.51991 | B16 9EE | 52.478 | -1.9341 | West Midlands
YIF - Ryde Town Council - 2022/3 |  | 42 | 1 | PO33 2NB | Completed | Green | 42 week program - considered generous | 10/07/2023 | 624706 | 474706 | 150000 | 153493.2 | 153087.8 | 405.4 | 0.32249 | PO33 2NB | 50.7317 | -1.1623 | South East
YIF - Merseyside play Action Council - 2023 |  | 62 | 1 | L3 5QF | Completed | Green | Applicant’s 52-week assessment is considered lengthy. Extensive roof redevelopment can be a timely activity which is included. | 01/08/2023 | 430167 | 367223 | 62944 | 378213.44 | 320654.44 | 57559 | 0.87319 | L3 5QF | 53.4089 | -2.9757 | North West
YIF - The Cooke E-Learning Foundation - 2023 |  | 17 | 1 | LE4 0RU | Completed | Green | 18 weeks start on site to completion | 04/08/2023 | 609050 | 509174 | 99876 | 583000.96 | 508758.03 | 74242.93 | 0.99918 | LE4 0RU | 52.6621 | -1.1537 | East Midlands
YIF - 105th Sheffield (High Green) Scout Group - 2023 |  | 34 | 1 | S35 3HY | Completed | Green |  | 21/08/2023 | 1842374 | 1812192 | 30182 | 988412.97 | 972123.23 | 16289.74 | 0.53644 | S35 3HY | 53.4752 | -1.4834 | Yorkshire and The Humber
YIF - Chichester Community Development Trust - 2023 |  | 16 | 1 | PO19 6AN | Completed | Green | 29 weeks start on site to completion | 23/08/2023 | 421375 | 355425 | 65950 | 345304 | 313354 | 31950 | 0.88163 | PO19 6AN | 50.8466 | -0.76901 | South East
YIF - NORTH EAST DANCE COMMUNITY INTEREST COMPANY - 2023 |  | 16 | 1 | SR6 0DT | Completed | Green | 18 weeks start on site to completion | 28/08/2023 | 864902 | 723302 | 141600 | 782247 | 723304 | 58943 | 1 | SR6 0DT | 54.9147 | -1.3773 | North East
YIF - Onside Grimsby - 2022 |  | 81 | 1 | DN31 1RS | In Progress | Red | DM-11/1- RAG rating changed project timeline - PC Aug ENHANCED MONITORING IN PLACE - WEEKLY LEADERSHIP REVIEW - Onside have taken possession of the site as of 04/09/23 – there has been some work to do in terms of clearing vegetation, setting up the sit | 04/09/2023 | 7945883 | 6794903 | 1150980 | 1908907 | 1835763 | 73144 | 0.27017 | DN31 1RS | 53.5671 | -0.087001 | Yorkshire and The Humber
YIF - The Montgomery Theatre and Arts Centre Ltd - 2023 |  | 12 | 1 | S1 2LG | Completed | Green | What is the project Duration? Works have started on site. 06/07 - Concerns identified around accuracy of costings. Increased from initial ask of £0.5m, to £1.2m approved at GC, to possibly another increase of £400k - throughness of costings and impact | 11/09/2023 | 1289379 | 1073879 | 215500 | 151188 | 101188 | 50000 | 0.094227 | S1 2LG | 53.3807 | -1.4691 | Yorkshire and The Humber
YIF - ENDEAVOUR TRAINING LIMITED - 2022 |  | 20 | 1 | S4 8FB | Completed | Green |  | 11/09/2023 | 1216826 | 1017756 | 199070 | 579729.67 | 538825 | 40904.67 | 0.52942 | S4 8FB | 53.4062 | -1.4397 | Yorkshire and The Humber
YIF - Lambton Street Youth & Community Hub - 2022 |  | 52 | 1 | SR4 6XA | Completed | Green | 58 week start on site to completion - started on site 11/9/23 | 11/09/2023 | 972956 | 864196 | 108760 | 657700 | 657700 | 0 | 0.76105 | SR4 6XA | 54.9058 | -1.4178 | North East
YIF - Shotton Parish Council - 2023 |  | 24 | 1 | DH6 2JL | In Progress | Green | DM- 23/10 -Ridge - Estimated construction duration from Start on Site to Construction Completion is 35 weeks. Therefore, the applicant’s 24-week assessment for the construction portion is below what Ridge would expect to see. | 18/09/2023 | 1232251 | 1026876 | 205375 | 776493 | 757433 | 28049 | 0.73761 | DH6 2JL | 54.7645 | -1.3956 | North East
YIF - 18th Darlington (1st Middleton St George) Scout Group - 2022 |  | 12 | 1 | DL2 1LD | Completed | Green | 21 weeks start on site to completion | 27/09/2023 | 404981 | 397981 | 7000 | 184850 | 177850 | 7000 | 0.44688 | DL2 1LD | 54.5134 | -1.4698 | North East
YIF - YMCA St Helens - 2023 |  | 22 | 1 | WA10 2TJ | Completed | Green | 30 week start on site to completion | 16/10/2023 | 1472851 | 1260578 | 212273 | 814790.2 | 756131.2 | 58659 | 0.59983 | WA10 2TJ | 53.4561 | -2.7389 | North West
YIF - Weymouth West Air Scout Group - 2023 |  | 52 | 1 | DT4 0SR | In Progress | Green | 52 week build considered lengthy by Ridge | 23/10/2023 | 873828 | 845628 | 28200 | 55057 | 50280 | 4777 | 0.059459 | DT4 0SR | 50.611 | -2.4832 | South West
YIF - AutismAble CIC - 2023 |  | 26 | 1 | NE33 1PD | Completed | Green |  | 31/10/2023 | 598870 | 478225 | 120645 | 369318 | 327545 | 60613 | 0.68492 | NE33 1PD | 54.9964 | -1.4308 | North East
YIF - SYA - 2022 |  | 26 | 1 | SY2 5RR | Completed | Green | 35 week start on site to completion Legal - now marked as green. Build - started on site and demo complete. Land works due to be complete by Xmas and SPI construction being delivered mid Jan. All on track for completion by end May '24. CFF and Build | 01/11/2023 | 1864990 | 1630322 | 234668 | 757401 | 715989 | 41412 | 0.43917 | SY2 5RR | 52.712 | -2.7228 | West Midlands
YIF - LINCOLNSHIRE Y.M.C.A. LTD - 2023 |  | 36 | 1 | LN2 4ND | Completed | Amber | 9 Month Build approx. Update 1/2/24 Call with group about revised build programme which suggested 31/3/25 deadline. Have suggested tender will have 31/12/24 deadline in it. Had planned to go out to tender 29/1 but has been delayed by one week and no | 06/11/2023 | 2015165 | 1682000 | 333165 | 195947 | 162630 | 33317 | 0.096688 | LN2 4ND | 53.2457 | -0.51645 | East Midlands
YIF - Fusion Health & Well Being - 2022/3 |  | 32 | 1 | DN32 9SW | In Progress | Green | DM- Gas report received ready to start on site Ridge review - applicant’s 32-week (8mths) assessment is considered reasonable. | 06/11/2023 | 1572804 | 1412271 | 160533 | 347163.08 | 337928.08 | 9235 | 0.23928 | DN32 9SW | 53.5573 | -0.066189 | Yorkshire and The Humber
YIF - Your Ideas LTD - 2022/3 |  | 24 | 1 | B98 7SX | Completed | Green | 27 weeks start on site to completion | 06/11/2023 | 1432870 | 1361610 | 71260 | 486243.39 | 457143.39 | 29100 | 0.33574 | B98 7SX | 52.2846 | -1.925 | West Midlands
YIF - YMCA North Staffordshire Ltd - 2022 |  | 52 | 1 | ST1 3AE | Completed | Amber | 52 weeks start on site to completion Legal & F21 complete. Update 31/1/24 BSR - application more complicated than initially thought so have bought in a specialist firm to assist with this. Meeting by 2/2 with national building inspector to see how B | 13/11/2023 | 2433915 | 2028848 | 405067 | 254331 | 235757 | 18574 | 0.1162 | ST1 3AE | 53.0176 | -2.1746 | West Midlands
YIF - 1st Hoveton and Wroxham Sea Scout Group - 2023 |  | 40 | 1 | NR12 8SF | In Progress | Green |  | 13/11/2023 | 1048315 | 986056 | 62259 | 213982.44 | 189863.36 | 24119.08 | 0.19255 | NR12 8SF | 52.7074 | 1.3995 | East of England
YIF - NORTH HUYTON COMMUNITIES FUTURE - 2023 |  | 30 | 1 | L14 9NQ | Completed | Green | 30 weeks start on site to completion | 27/11/2023 | 976889 | 853589 | 123300 | 221528.29 | 192546.29 | 28982 | 0.22557 | L14 9NQ | 53.4238 | -2.8642 | North West
YIF - 14th Hove (St Andrews Portslade) Scout Group - 2023 |  | 48 | 1 | BN41 1DE | In Progress | Green | DM 20/12 - the applicant’s 14-week build assessment is considered ambitious, but not necessarily unachievable. | 30/11/2023 | 204456 | 197219 | 7237 | 0 | 0 | 0 | 0 | BN41 1DE | 50.8324 | -0.21185 | South East
YIF - YMCA FAIRTHORNE GROUP - 2023 |  | 15 | 1 | SO14 0AW | Completed | Green | 14 weeks start on site to completion | 04/12/2023 | 326946 | 272619 | 54327 | 205000 | 205000 | 0 | 0.75197 | SO14 0AW | 50.9115 | -1.3953 | South East
YIF - Stanley Events Ltd - 2022 |  | 42 | 1 | DH9 6PZ | Completed | Green | 42 weeks start on site to completion | 11/12/2023 | 1392677 | 1364677 | 28000 | 156947.91 | 139297.91 | 17650 | 0.10207 | DH9 6PZ | 54.8629 | -1.6979 | North East
YIF - OAC Buildings - 2022 |  | 16 | 1 | S11 7TG | In Progress | Green | Ridge anticipate 18 week build | 11/12/2023 | 656334 | 550173 | 106161 | 132110.56 | 117573 | 14538 | 0.2137 | S11 7TG | 53.3579 | -1.5382 | Yorkshire and The Humber
YIF - Plymouth Argyle Football in the Community Trust - 2023 |  | 52 | 1 | PL1 4NE | In Progress | Amber | 6/12/23 -DM Gas report received 24/10-DM-Shortfall in Budget.- RM arranging call with all stakeholders to consider appropriate way forward. F21 - Two stage tender process - Anticipate GAS report to be issued Q4 Jan Ridge : estimated construction durati | 02/01/2024 | 1931755 | 1756000 | 175755 | 0 | 0 | 0 | 0 | PL1 4NE | 50.3711 | -4.1722 | South West
YIF - BBGC - 2023 |  | 28 | 1 | BB10 1JQ | Completed | Green | 29 weeks start on site to completion | 02/01/2024 | 973996 | 863996 | 110000 | 148503.35 | 124462.7 | 24040.65 | 0.14405 | BB10 1JQ | 53.8029 | -2.2362 | North West
YIF - Positive Futures North Liverpool - 2023 |  | 26 | 1 | L13 9DY | In Progress | Green | DM 29/1/24 - Gas report received today. 28 weeks start on site to completion | 02/01/2024 | 1081873 | 932713 | 149160 | 219351 | 215863 | 34888 | 0.23144 | L13 9DY | 53.434 | -2.9386 | North West
YIF - Netherley Youth and Community Initiative - 2023 |  | 46 | 1 | L27 8XR | Completed | Green | 20/10 - DM - ready to start contractor in place- prioritise legal DD | 08/01/2024 | 2687572 | 2252211 | 435361 | 168223 | 93363 | 74860 | 0.041454 | L27 8XR | 53.3909 | -2.8365 | North West
YIF - YMCA Trinity Group - 2022 |  | 50 | 1 | PE3 8DX | In Progress | Green | DM 22/12 - Procurement completed- Gas report issued. ENHANCED MONITORING IN PLACE - WEEKLY LEADERSHIP REVIEW - Legal Charge outstanding - 50 week construction timeline. F21 - Two stage tender process - Anticipate GAS report to be issued Q3 Dec Start | 08/01/2024 | 5124000 | 4974000 | 150000 | 490475.72 | 458848.72 | 31627 | 0.092249 | PE3 8DX | 52.5892 | -0.28358 | East of England
YIF - the garage trust - 2022 |  | 25 | 1 | NR2 1NY | Completed | Green |  | 08/01/2024 | 462500 | 275000 | 187500 | 248371.02 | 108012.26 | 140358.76 | 0.39277 | NR2 1NY | 52.6284 | 1.2874 | East of England
YIF - THE BRAUNSTONE FOUNDATION - 2023 |  | 10 | 1 | LE3 1QZ | Completed | Green |  | 08/01/2024 | 588113 | 494913 | 93200 | 239574.8 | 199585 | 39990 | 0.40327 | LE3 1QZ | 52.6294 | -1.1818 | East Midlands
YIF - Wellspring Settlement - 2023 |  | 24 | 1 | BS5 9NB | Completed | Green | 18 weeks start on site to completion | 08/01/2024 | 796647 | 714713 | 81934 | 418974 | 387180 | 31794 | 0.54173 | BS5 9NB | 51.4563 | -2.5634 | South West
YIF - Tiber Community Building - 2023 |  | 40 | 1 | L8 0TP | In Progress | Green | 52 week build considered reasonable Price of contractor is higher than YIF capital budget if VAT is included- need to address prior to signing contract with Krol Collett. Grantee provided copy of VAT advice. Plan to reclaim VAT as did with Phase1 build | 15/01/2024 | 3578949 | 3069470 | 509479 | 43778 | 20376 | 23402 | 0.0066383 | L8 0TP | 53.3935 | -2.9494 | North West
YIF - Fleetwood Trust - 2023 |  | 34 | 1 | FY7 6BE | Completed | Green | 34 weeks start on site to completion Contract states: start date 15/01/24; 18 wk programme due to complete 24/05/24. | 15/01/2024 | 1070443 | 893880 | 176563 | 134512 | 119214 | 15298 | 0.13337 | FY7 6BE | 53.9262 | -3.0093 | North West
YIF - The Florence Institute Trust - 2023 |  | 16 | 1 | L8 4RF | Completed | Green | DM 3/1/24 - GAS report circulated and added to record DM 17/10 - The applicant’s 16-week assessment is considered slightly low. | 15/01/2024 | 834000 | 695000 | 139000 | 404838 | 356756 | 48082 | 0.51332 | L8 4RF | 53.3836 | -2.9686 | North West
YIF - The Lowdown - 2022 |  | 40 | 1 | NN1 1PP | Completed | Green | 40 weeks start on site to completion | 17/01/2024 | 1292064 | 919784 | 372280 | 164843.48 | 65733.2 | 99110.28 | 0.071466 | NN1 1PP | 52.2365 | -0.89761 | East Midlands
YIF - Onside Salford - 2022 |  | 60 | 1 | M6 5EJ | In Progress | Red | 10/1/24- Progress Meeting with AP/FN - DM notes from Meeting -Anticipated Start Date revised to 29th January 24 - Anticipated Practical Completion 28th April 2025. Progress Report to be issued by Onside. Project now RAG rated Red. ENHANCED MONITORING I | 29/01/2024 | 7582651 | 6531750 | 1050901 | 771841 | 580220 | 191621 | 0.088831 | M6 5EJ | 53.4878 | -2.2813 | North West
YIF - Cleethorpes Community Sports and Education - 2023 |  | 36 | 1 | DN35 8UN | Completed | Green | 30/1/24 - DM - Gas report Received The applicant’s 36-week assessment is considered ambitious. Ridge advise more likely 41 weeks F21 report due Jan 24 | 31/01/2024 | 2647230.57 | 2333458 | 313772.57 | 179127.11 | 131811.2 | 47315.91 | 0.056487 | DN35 8UN | 53.5543 | -0.03678 | Yorkshire and The Humber
YIF - St Michael's Centre Partnership, Byker - 2023 |  | 60 | 1 | L26 1TT | In Progress | Amber | ENHANCED MONITORING IN PLACE - WEEKLY LEADERSHIP REVIEW - 08/09 - lease still outstanding - 62 week build plus 12 week tender. End Oct deadline for lease resolution | 01/02/2024 | 4427163 | 4122385 | 304778 | 442390 | 402432 | 39958 | 0.097621 | L26 1TT | 53.3574 | -2.8377 | North West
YIF - Blackbridge Charitable Community Benefit Society Limited - 2023 |  | 49 | 1 | GL1 5TX | In Progress | Amber | DM 24/1/24- Start date has changed from 29/01 to 05/02. The lease with Gloucester City Council and the building contract with EG Carter will be signed this week. ENHANCED MONITORING- 59 weeks start on site to completion based on Ridge Assessment. (Ci | 05/02/2024 | 2846521 | 2617721 | 228800 | 0 | 0 | 0 | 0 | GL1 5TX | 51.8429 | -2.2531 | South West
YIF - SOAR Community - 2023 |  | 18 | 1 | S5 8BB | In Progress | Green | 30/10 -DM- Ridge anticipate Start on Site to Construction Completion is 36 weeks. Applicant’s 24-week assessment is considered shorter than expected. | 07/02/2024 | 1479461 | 1232884 | 246577 | 0 | 0 | 0 | 0 | S5 8BB | 53.4202 | -1.4806 | Yorkshire and The Humber
YIF - Murrayside Community Development CIC - 2023 |  | 32 | 1 | IP3 9JL | In Progress | Green | Ridge Assessment 37 week build, Grantee assessment start Feb -Dec 24 completion | 08/02/2024 | 1646500 | 1372500 | 274000 | 19200 | 9200 | 10000 | 0.0067031 | IP3 9JL | 52.042 | 1.1844 | East of England
YIF - Friction Arts Ltd. - 2023 |  | 42 | 1 | B12 0QH | Completed | Amber | Anticipated Build duration 50 weeks, - new timeline given by PM is 36 weeks - on site on 9 Feb 24 finished 18/10/24. Post Procurement negotiation and VE taking place week of 15 Jan 24. | 12/02/2024 | 1115772 | 1034800 | 80972 | 94280 | 84381 | 9899 | 0.081543 | B12 0QH | 52.4719 | -1.8854 | West Midlands
YIF - THE HIGHLIFE CENTRE LTD - 2023 |  | 36 | 1 | CV2 4LY | In Progress | Green | 23/10 -DM Ridge estimate is 15 to 20 weeks build. Therefore, the applicant’s 36-week assessment is considered lengthy. | 12/02/2024 | 409417 | 351237 | 58180 | 114368 | 104672 | 9696 | 0.29801 | CV2 4LY | 52.4157 | -1.4826 | West Midlands
YIF - Bridlington Club For Young People - 2023 |  | 12 | 1 | YO16 4AY | Completed | Green |  | 19/02/2024 | 1111160 | 992160 | 119000 | 156985 | 156985 | 0 | 0.15823 | YO16 4AY | 54.0909 | -0.2133 | Yorkshire and The Humber
YIF - KBSK PERFORMING ARTS CIC - 2022 |  | 20 | 1 | PL31 1DS | In Progress | Green | DM 29/1/24- Anticipated Start -26th Feb with - 2 Months build in factory and 6 weeks build on site. - 14 weeks Total. NB. Grantee to pay • Deposit: 30 % of the full contract value is due upon receipt of your order • Interim 1: 20 % of the full cont | 26/02/2024 | 718483.9 | 630733.9 | 87750 | 0 | 0 | 0 | 0 | PL31 1DS | 50.4666 | -4.7127 | South West
YIF - The Boathouse Youth Limited - 2023 |  | 20 | 1 | FY3 7EA | In Progress | Green | DM 1/2/24 - Contractor ready to start Licence for alterations, Lease to resolve. 20 weeks start on site to completion | 26/02/2024 | 487975 | 412975 | 75000 | 0 | 0 | 0 | 0 | FY3 7EA | 53.8308 | -3.0086 | North West
YIF - Merseyside Youth Association Ltd - 2023 |  | 10 | 1 | L20 4QJ | Completed | Green | DM 25/1/24 - Report from RM -Delay on Merseyside Youth Association by 4 weeks – Naomi has done a progress report. Reviewed site commencement date and this down as 26/02/2024 30 week duration considered reasonable | 26/02/2024 | 1593757 | 1403900 | 189857 | 12131.41 | 6240 | 5891 | 0.0044448 | L20 4QJ | 53.4588 | -3.0084 | North West
YIF - Hartlepool Borough Council - Rossmere Youth Club |  | 28 | 1 | TS25 5EB | Completed | Green | 32 weeks start on site to completion | 26/02/2024 | 1265037 | 1186979 | 78058 | 35278.5 | 35278.5 | 0 | 0.029721 | TS25 5EB | 54.6614 | -1.2341 | North East
YIF - The Foxton Centre - 2023 |  | 52 | 1 | PR1 3SA | Completed | Green | 40 weeks start on site to completion | 26/02/2024 | 2459627 | 2055000 | 404627 | 175437.04 | 127230 | 48207.04 | 0.061912 | PR1 3SA | 53.7564 | -2.6938 | North West
YIF - Sharrow Community Forum |  | 48 | 1 | S7 1BJ | Completed | Green | From Progress report PR-00004429- 36 weeks build due to use of CLT construction 56 weeks start on site to completion 25/01/24 - NS - 3 submitted bids 30% over YIF budget. Need for VE and re-design work. 2 contractors still interested in job. | 29/02/2024 | 2670829 | 2445304 | 225525 | 299301.81 | 230234.52 | 69067.29 | 0.094154 | S7 1BJ | 53.3661 | -1.4754 | Yorkshire and The Humber
YIF - 1st Buxted (O'Brien's Own) Scout Group - 2023 |  | 26 | 1 | TN22 5FD | In Progress | Green | 23/10 -DM -the estimated construction duration from Start on Site to Construction Completion is 28 weeks | 01/03/2024 | 950981 | 946981 | 4000 | 0 | 0 | 0 | 0 | TN22 5FD | 50.9894 | 0.13209 | South East
YIF - Knowsley Metropolitan Borough Council (Tower Hill) - 2023 |  | 26 | 1 | L33 1WU | Completed | Green | 26 weeks start on site to completion | 01/03/2024 | 1661755 | 1384796 | 276959 | 137015 | 26231 | 110784 | 0.018942 | L33 1WU | 53.4937 | -2.8883 | North West
YIF - Swanscombe and Greenhithe Town Council - 2023 |  | 56 | 1 | DA10 0AD | In Progress | Amber | ENHANCED MONITORING IN PLACE - WEEKLY LEADERSHIP REVIEW - 61 weeks start on site to completion plus 12 week tender. Access road issues remain outstanding and unlikely resolved in time Update 30/1/24 Legal - Deed of easement now agreed by all 3 parties | 04/03/2024 | 4385174 | 4385174 | 0 | 0 | 0 | 0 | 0 | DA10 0AD | 51.4478 | 0.30876 | South East
YIF - 1st Shelton Lock Scout and Guide Group - 2023 |  | 43 | 1 | DE24 9QX | In Progress | Green | 47 weeks start on site to completion | 04/03/2024 | 1241806 | 1231806 | 10000 | 0 | 0 | 0 | 0 | DE24 9QX | 52.8767 | -1.4488 | East Midlands
YIF - Al-Ghazali Multicultural Centre - 2023 |  | 34 | 1 | L7 6HA | Completed | Green |  | 04/03/2024 | 1401968 | 1296968 | 105000 | 16117 | 2335 | 13781.68 | 0.0018004 | L7 6HA | 53.3987 | -2.9486 | North West
YIF - Moss side Millennium Powerhouse LTD - 2023 |  | 27 | 1 | M14 4SL | In Progress | Green | 30/10 - DM - Ridge Assessment the applicant’s 27- or 30-week assessment is considered reasonable | 04/03/2024 | 2781086 | 2461605 | 319481 | 80824 | 70144 | 10680 | 0.028495 | M14 4SL | 53.4576 | -2.2417 | North West
YIF - 2nd Maryport Scout Group - 2023 |  | 44 | 1 | CA15 6DT | Completed | Green | DM 20/12 - 9 Month Build. DPS - Tender documents being drafted | 15/03/2024 | 948513 | 826013 | 122500 | 42597 | 42597 | 0 | 0.051569 | CA15 6DT | 54.7132 | -3.4997 | North West
YIF - Investing in Children CiC - 2022 |  | 59 | 1 | DH2 3QJ | In Progress | Amber | DM 21/12 - RM site visit Jan24 so RAG rating can be reviewed following this Update 1/2/24 The main tender was due back by 22/1 but has just been extended by a week so due back end January. Tender update - 6 received back in total with bids ranging f | 15/03/2024 | 1638500 | 1571000 | 67500 | 123750 | 105000 | 18750 | 0.066836 | DH2 3QJ | 54.8192 | -1.5972 | North East
YIF - Sunderland Bangladesh International Centre - 2022 |  | 14 | 1 | SR1 2QE | Completed | Green | DM 25/1/24 - 80K VE to be completed - Vat DM 24/01/24 - E Mail from F21 -SBIC site start 18/03/2024 and PC date of 30/09/2024. DM 21/12 - DPS tender report received. 22 weeks start on site to completion 9/10/23 - now suggesting 9 month from s | 18/03/2024 | 1483437 | 1383437 | 100000 | 164460 | 119227 | 45233 | 0.086182 | SR1 2QE | 54.9042 | -1.3767 | North East
YIF - Youth Options Ltd - 2023 |  | 16 | 1 | SO16 9RS | Completed | Green | 23/10- DM-Applicants 32-week assessment is considered reasonable. | 18/03/2024 | 1289009 | 1075496 | 213513 | 201225 | 163549 | 37676 | 0.15207 | SO16 9RS | 50.9283 | -1.4599 | South East
YIF - Projects4Change - 2023 |  | 26 | 1 | NE5 3UT | In Progress | Green | 29 weeks start on site to completion | 20/03/2024 | 872382 | 727181 | 145201 | 39285 | 32758 | 6527 | 0.045048 | NE5 3UT | 54.9978 | -1.6571 | North East
YIF - Services for Young People Hertfordshire County Council - 2022 |  | 20 | 1 | EN8 7DJ | Completed | Green | DM -17/10 -The applicant’s 20-week assessment is considered ambitious - 6-7 months (26-30 weeks) more realistic. DM - 17/10 - Update from GA: We hope to go out to tender around mid- October 2023 with a view to appoint a contractor early 2024, with a st | 21/03/2024 | 1025830 | 855830 | 170000 | 30000 | 30000 | 0 | 0.035054 | EN8 7DJ | 51.688 | -0.032073 | East of England
YIF - Nudge Community Builders - 2023 |  | 20 | 1 | PL1 3EY | In Progress | Green | Two projects - (1) the Millennium Building - 23 weeks and (2) Building C103 - 32 weeks. Ridge assessment - only one project - The Millennium Building was funded by YIF. | 25/03/2024 | 466900 | 400200 | 66700 | 30500 | 24000 | 6500 | 0.05997 | PL1 3EY | 50.37 | -4.1505 | South West
YIF - Isle of Wight Council - 2023 |  | 59 | 1 | PO36 8JJ | Completed | Amber | 11/10 -DM - Ridge confirm the applicant’s 50-week assessment is considered reasonable. Enhanced Monitoring in Place | 29/03/2024 | 3110090 | 2862190 | 247900 | 78902 | 78902 | 0 | 0.027567 | PO36 8JJ | 50.6547 | -1.1577 | South East
YIF - Garston Adventure Playground Ltd - 2023 |  | 23 | 1 | L19 1QP | Completed | Green | DM 19/12 - Ridge assessment of program 25 weeks reasonable. Construction Costs/m2 at Mean to High End, and Passivhaus standard which could be cost prohibitive. Keep an eye on this. | 29/03/2024 | 1370696 | 1234711 | 135985 | 168773 | 144417 | 24356 | 0.11696 | L19 1QP | 53.3579 | -2.902 | North West
YIF - YMCA Taunton - 2023 |  | 40 | 1 | TA1 2LB | In Progress | Amber | 8/11 - Amber rating applied due to challenging timetable and limited progress beyond planning consent. 45 weeks start on site to completion | 30/03/2024 | 2107714 | 1756429 | 351285 | 9449 | 4124 | 5325 | 0.0023479 | TA1 2LB | 51.015 | -3.0809 | South West
YIF - Crewe Youth Club - 2023 |  | 26 | 1 | CW1 2AZ | Completed | Green | DM- Ridge Review 25 week Build. Programme timeline slipped 12 wks - not due to be on site until April 24. Could frontload YIF funding before Towns Fund - cash flow to be reviewed with the QS, VAT has been not been included in grant request as CYC thoug | 01/04/2024 | 765231 | 715031 | 50200 | 0 | 0 | 0 | 0 | CW1 2AZ | 53.0996 | -2.4363 | North West
YIF - Ten Count Boxing Gym CIO - 2023 |  | 16 | 1 | ST2 0LL | In Progress | Green | 20 weeks start on site to completion | 01/04/2024 | 959120 | 879120 | 80000 | 0 | 0 | 0 | 0 | ST2 0LL | 53.0128 | -2.1251 | West Midlands
YIF - Newground Together - 2023 |  | 12 | 1 | BB1 2RH | In Progress | Green | Ridge estimate 29 week program - Circa 7/8 month program | 01/04/2024 | 620139 | 552727 | 67412 | 0 | 0 | 0 | 0 | BB1 2RH | 53.7385 | -2.4459 | North West
YIF - Essex Boys and Girls Clubs - 2023 |  | 26 | 1 | SS1 2QQ | In Progress | Amber | DM - 18/1/24- Anticipated Start date and revised project timeline of 26 week DM - 8/11- Amber rated - No planning submitted or RIBA stage 4 as yet. 38 weeks start on site to completion | 01/04/2024 | 1500000 | 1400000 | 100000 | 0 | 0 | 0 | 0 | SS1 2QQ | 51.5402 | 0.73823 | East of England
YIF - Oxford City Council - 2023 |  | 34 | 1 | OX4 6JL | Completed | Green | 29/1/24 - DM- Intend to start on site Apr-24, finish Oct-24. GAS report in progress 30 weeks start on site to completion | 01/04/2024 | 1344106 | 1120199 | 223907 | 3000 | 3000 | 0 | 0.0026781 | OX4 6JL | 51.7197 | -1.1984 | South East
YIF - CENTRE4 LIMITED - 2023 |  | 40 | 1 | DN33 1HE | In Progress | Green | Ridge anticipate 43 weeks build (circa11months). Applicant assessment is 40 week project duration. | 01/04/2024 | 2846291 | 2378230 | 468061 | 125910 | 80021 | 45889 | 0.033647 | DN33 1HE | 53.5476 | -0.10823 | Yorkshire and The Humber
YIF - 33rd Norwich Scout Group - 2023 |  | 35 | 1 | NR2 3JF | Completed | Green | DM 26/1/24 - The lowest tender after adjustment is TM Browne Ltd who have proposed a 39wks build period and tender price of £1,490,915.10. VE work critical DM - Note from RM - tender quotes that have come back from 33rd Norwich Scout Group. They’ve a | 01/04/2024 | 915609 | 909939 | 5670 | 34880 | 33380 | 1500 | 0.036684 | NR2 3JF | 52.6245 | 1.2685 | East of England
YIF - ALL SAINTS COMMUNITY DEVELOPMENT COMPANY - 2023 |  | 48 | 1 | B14 7RA | In Progress | Green | DM - Now 34 week program Planning Mid Feb DM -17/10- Ridge Assessment - 48 week build reasonable Update 30/1/24 Legal - Issues with Unity appear to now be resolved. Waiting for paperwork from Big Lottery. BCC delayed as unable to find correct cont | 01/04/2024 | 3130220 | 2851535 | 278685 | 120000 | 120000 | 0 | 0.042083 | B14 7RA | 52.4321 | -1.8951 | West Midlands
YIF - Blackburn Youth Zone - 2023 |  | 20 | 1 | BB1 1EP | Completed | Green | 30 weeks start on site to completion | 01/04/2024 | 3094268 | 2890268 | 204000 | 184690.52 | 131107.05 | 53583.47 | 0.045362 | BB1 1EP | 53.7461 | -2.4819 | North West
YIF - NO LIMITS (SOUTH) - 2023 |  | 16 | 1 | SO17 1XN | Completed | Green | 22 weeks start on site to completion | 01/04/2024 | 689894 | 594204 | 95689 | 30000 | 30000 | 0 | 0.050488 | SO17 1XN | 50.9181 | -1.4029 | South East
YIF - Brighton Youth Centre - 2022 |  | 80 | 1 | BN2 0JR | In Progress | Amber | Fusion 21 notes - Have re-designed, 2 options, tender for both options at same time to avoid further delays. Ridge have reviewed revised program - 62 weeks. Start on site essential by 23/10/23 | 01/04/2024 | 6323200 | 5176200 | 1147000 | 910688.93 | 589118.67 | 321570.26 | 0.11381 | BN2 0JR | 50.8222 | -0.13048 | South East
YIF - Middleport Matters Community Trust - 2023 |  | 22 | 1 | ST6 3PT | In Progress | Green | 30/10 -DM - Ridge advise the estimated construction duration from Start on Site to Construction Completion is 25 weeks. | 04/04/2024 | 413374 | 357380 | 55994 | 0 | 0 | 0 | 0 | ST6 3PT | 53.0391 | -2.2053 | West Midlands
YIF - Onside South Bristol - 2022 |  | 60 | 1 | BS4 1XD | In Progress | Red | Practical completion anticipated - April 2025 but delays push to June 2025 Delays with the Council putting access road in have meant that they have been unable to start onsite. Bell mouth access will be put in place but potentially this pushes dates ba | 05/04/2024 | 8853739 | 7461449 | 1392290 | 746883 | 436883 | 310000 | 0.058552 | BS4 1XD | 51.4172 | -2.5961 | South West
YIF - ELOQUENT PRAISE AND EMPOWERMENT DANCE COMPANY CIC - 2023 |  | 6 | 1 | B6 5RW | Completed | Green | 30/10-DM- Ridge assessment applicant’s 22-week assessment is considered reasonable. | 08/04/2024 | 470880 | 392400 | 78480 | 26540 | 20000 | 6540 | 0.050968 | B6 5RW | 52.4989 | -1.8825 | West Midlands
YIF - The Warren of Hull Limited - 2023 |  | 35 | 1 | HU1 3DR | In Progress | Amber | 23/10 -DM RAG rating changed as per notes below Enhanced Monitoring Required. 20/10 -NS- Risk more like Red as project 12 wks behind schedule, lease yet to be signed (with Hull CC), & Ridge report highlights 39 wk build prog 10/01 NS ITT delayed 3w due | 08/04/2024 | 1865653 | 1636061 | 229592 | 103170 | 103170 | 0 | 0.06306 | HU1 3DR | 53.7451 | -0.33747 | Yorkshire and The Humber
YIF - Reading Central District Scout Council - 2023 |  | 26 | 1 | RG2 7HG | Completed | Amber | DM 10/1/24- Tender pushed back Anticipated Start on site date 15th April with 9 month anticipated build. DM 19/12 - Programme applicants 28 week assessment considered short, Ridge estimate 36 weeks. Construction Costs @1,827/m2 which is between th | 15/04/2024 | 1834386 | 1834386 | 0 | 0 | 0 | 0 | 0 | RG2 7HG | 51.4356 | -0.95092 | South East
YIF - 35th Derby (Markeaton) Scout Group - 2023 |  | 24 | 1 | DE1 3SP | In Progress | Green | 30/10 -DM- Ridge advise the estimated construction duration from Start on Site to Construction Completion is 25 weeks | 15/04/2024 | 414870 | 400560 | 14310 | 0 | 0 | 0 | 0 | DE1 3SP | 52.9313 | -1.493 | East Midlands
YIF - HAFWAY - 2023 |  | 16 | 1 | BL1 8BP | Completed | Green | 23/10-DM- Ridge comments proposed 27-week programme ambitious, but not necessarily unachievable. 26/01- NS: ITT not going out until 06/02/24; on site 15/04/24 but still 16 wk refurb programme (complet 05/08/24). | 15/04/2024 | 1503072 | 1351476 | 151596 | 28092 | 24912 | 3180 | 0.018433 | BL1 8BP | 53.5955 | -2.4476 | North West
YIF - 1st belton scout group - 2023 |  | 12 | 1 | NR31 9LU | In Progress | Green |  | 15/04/2024 | 292243.2 | 267243.2 | 25000 | 9839 | 9839 | 0 | 0.036817 | NR31 9LU | 52.5615 | 1.6558 | East of England
YIF - Newcastle upon Tyne Y.M.C.A. - 2023 |  | 20 | 1 | NE6 4JL | Completed | Green | DM - Planning Due Dec 23 - Update required 20 weeks start on site to completion | 15/04/2024 | 507823 | 424000 | 83823 | 113166 | 113166 | 0 | 0.2669 | NE6 4JL | 54.9761 | -1.549 | North East
YIF - The Manchester Youth Zone Ltd - 2023 |  | 16 | 1 | M9 8AE | In Progress | Green | DM 27/10 - Ridge Assessment -The estimated construction duration from Start on Site to Construction Completion is 25 weeks. Therefore, the applicant’s 17-week assessment is considered shorter than expected DM 27/10 - Anticipated start date on record is J | 19/04/2024 | 1612036 | 1402582 | 209454 | 0 | 0 | 0 | 0 | M9 8AE | 53.5146 | -2.2132 | North West
YIF - YMCA BRUNEL GROUP - 2023 |  | 22 | 1 | BA11 3EF | Completed | Green | Costs & Planning to Check note comments in Ridge Report | 22/04/2024 | 804668 | 712016 | 92652 | 5900 | 5900 | 0 | 0.0082863 | BA11 3EF | 51.2346 | -2.3326 | South West
YIF - Onside Crewe - 2022 |  | 60 | 1 | CW2 7BX | In Progress | Red | DM 15/1/24 - Program received from Lee Williamson - Anticipated Start Date - 22/4/25 Anticipated PC Date 14/7/25 10/01/24 Delays to start date as stopping up request which went in on October has been reviewed with the feedback that they have 34 other | 22/04/2024 | 8295058 | 6999215 | 1295843 | 736312 | 575512 | 160800 | 0.082225 | CW2 7BX | 53.0947 | -2.4411 | North West
YIF - 61st Doncaster(Bentley) Air Scout Group - 2023 |  | 32 | 1 | DN5 0RS | Completed | Green | 32 weeks start on site to completion | 26/04/2024 | 1346270 | 1121893 | 224377 | 30123.74 | 4850 | 25273.74 | 0.0043231 | DN5 0RS | 53.548 | -1.1447 | Yorkshire and The Humber
YIF - London Borough of Barking and Dagenham - 2023 |  | 40 | 1 | RM6 5BJ | Completed | Green |  | 29/04/2024 | 2098374 | 1974874 | 123500 | 226426.88 | 194228.95 | 32197.93 | 0.09835 | RM6 5BJ | 51.5834 | 0.13076 | London
YIF - 1st Norton on Tees Scout Group - 2023 |  | 26 | 1 | TS20 1GE | Completed | Green | DM 20/12- Applicant’s 26-week Build assessment is reasonable although slightly excessive. | 01/05/2024 | 336182 | 336182 |  | 5600 | 5600 | 0 | 0.016658 | TS20 1GE | 54.5945 | -1.3059 | North East
YIF - Blackpool Council - 2023 |  | 30 | 1 | FY1 3JW | In Progress | Amber | DM 8/1/24- RAG rating changed to Amber as procurement will not be completed until May and 9 month Build finishing in Jan 25. Project is due to be completed by 31 Dec 24 - RAG - Green Ridge Estimate - Max 37 week build. Deadline for starting on si | 06/05/2024 | 1688650 | 1499290 | 189360 | 0 | 0 | 0 | 0 | FY1 3JW | 53.8212 | -3.0431 | North West
YIF - Ocean Road Centre - 2023 |  | 43 | 1 | NE33 2DW | Completed | Green | ENHANCED MONITORING IN PLACE - 25/10 -DM - Two stage tender Process discussed on call F21 informed. 11/10 - At Riba Stage 3 - Start on site March 24 with 43 week build. | 06/05/2024 | 2287228 | 2098600 | 188628 | 42000 | 42000 | 0 | 0.020013 | NE33 2DW | 54.9996 | -1.4294 | North East
YIF - BRONTE YOUTH & COMMUNITY CENTRE - 2023 |  | 39 | 1 | L3 5NB | In Progress | Amber | DM - 1/2/24 - Pretender estimate 170k, Grantee advises 7 month build, start in May with Late Dec Finish 9/10 - Ridge Assessment -10 Month Build realistic 27/09 - EMAIL FROM FM TO CH - Out to tender January 2024; Start on site April 2024; Finishing Dec | 08/05/2024 | 4145525 | 3454604 | 690921 | 309550 | 207138 | 102412 | 0.05996 | L3 5NB | 53.4064 | -2.9724 | North West
YIF - CEDE FOUNDATION - 2023 |  | 30 | 1 | M5 3RG | Completed | Amber | DM 11/12- Grantee has capacity issues, design not advanced, PM appointed and Grantee's Architect brought back onto team. Planning deadline March 24 DM 11/10 - RM advised Procurement will take 3 Months Applicant’s 30-week assessment is considered ambit | 10/05/2024 | 785554 | 655646 | 129908 | 0 | 0 | 0 | 0 | M5 3RG | 53.4756 | -2.2741 | North West
YIF - DROP ZONE YOUTH PROJECTS LTD. - 2023 |  | 28 | 1 | LA14 1XL | In Progress | Green | 28 weeks start on site to completion | 15/05/2024 | 607636 | 541644 | 65992 | 0 | 0 | 0 | 0 | LA14 1XL | 54.1135 | -3.2328 | North West
YIF - Double Six Youth Club - 2023 |  | 30 | 1 | S8 8TE | Completed | Green | 8 weeks for procurement noted - reasonable 28-week construction assessment is considered reasonable The applicant has stated a commencement date of 01/03/2024 and an end date of 09/09/2024. Subject to the applicant meeting these planned dates, this | 16/05/2024 | 1504459 | 1438398 | 66061 | 84408 | 84408 | 0 | 0.058682 | S8 8TE | 53.3467 | -1.4778 | Yorkshire and The Humber
YIF - TOKKO LTD - 2023 |  | 21 | 1 | LU1 2QP | In Progress | Amber | Rated Amber at RM request - awaiting update | 31/05/2024 | 1365799 | 1159799 | 206000 | 0 | 0 | 0 | 0 | LU1 2QP | 51.8806 | -0.41849 | East of England
YIF - Torbay Council - 2022/3 |  | 35 | 1 | TQ2 8ET | In Progress | Green | Planning for external windows only with no neighbours, highly likely to be approved and this will be the last part of the job, allowing the project to proceed and giving a window of 12 months for approval. | 03/06/2024 | 625995 | 528447 | 97548 | 0 | 0 | 0 | 0 | TQ2 8ET | 50.4892 | -3.5366 | South West
YIF - 1st Burnmoor Scout Group - 2023 |  | 22 | 1 | DH4 6AW | In Progress | Green | 24 Week build, 8% Contingency Low. | 03/06/2024 | 1237879 | 1212879 | 25000 | 0 | 0 | 0 | 0 | DH4 6AW | 54.8483 | -1.5124 | North East
YIF - Liberty Jamboree - 2023 |  | 26 | 1 | WS13 7PZ | In Progress | Amber | DM- 14/11- 37 week build assessment from Ridge Lease deadline to be considered - Ongoing negotiations with Sport England re a potential pre-commencement or pre-occupation requirement to install new cricket nets on the site: if Sport England are stubbo | 03/06/2024 | 1900270 | 1584600 | 315670 | 0 | 0 | 0 | 0 | WS13 7PZ | 52.6969 | -1.8363 | West Midlands
YIF - Swindon Borough Council - 2023 |  | 36 | 1 | SN3 2RW | Completed | Amber | DM - 25/1/24 - PC 20th March 2025 F21 - Contract award is 14/06/2024-27/06/2024 so the estimated date for the GAS report to be issued is July 2024. NOW SUBJECT TO ENHANCED MONITORING WITH LEADERSHIP TEAM - Project due to complete in Feb/Mar '25. Ri | 06/06/2024 | 3766099 | 3241267 | 524832 | 50224 | 19000 | 31224 | 0.0058619 | SN3 2RW | 51.5592 | -1.7487 | South West
YIF - Rea Valley District Scouts - 2023 |  | 25 | 1 | B32 3PN | In Progress | Green | Ridge 34 week build reasonable | 15/06/2024 | 1172790 | 1160790 | 12000 | 0 | 0 | 0 | 0 | B32 3PN | 52.4381 | -2.0046 | West Midlands
YIF - 1ST HEALING SCOUT GROUP GRIMSBY AND CLEETHORPES DISTRICT - 2023 |  | 20 | 1 | DN41 7RD | In Progress | Green | Ridge advice 30 week program (7.5m) is realistic 24/01/24 - NS - call with PM confirmed programme timeline is achievable; Tender to specify completion deadline Dec 24 | 17/06/2024 | 730833 | 720753 | 10080 | 54068.8 | 45157.33 | 8911.47 | 0.062653 | DN41 7RD | 53.5813 | -0.16514 | Yorkshire and The Humber
YIF - Green Lane Masjid and Community Centre - 2023 |  | 52 | 1 | B9 5DB | In Progress | Green | 38 weeks start on site to completion |  | 2185326 | 1876786 | 308540 | 0 | 0 | 0 | 0 | B9 5DB | 52.4732 | -1.8627 | West Midlands
YIF - The Music Works (charity) - 2023 |  | 16 | 1 | GL14 2SB | Completed | Green | DM 23/10- Start on Site to Construction Completion is 22 weeks. Therefore, the applicant’s 16-week assessment is considered ambitious. | 23/10/2023 | 983413 | 823413 | 160000 | 228945 | 228945 | 0 | 0.27804 | GL14 2SB | 51.8241 | -2.4995 | South West
YIF - INSPIRE SUFFOLK LTD - 2023 |  | 30 | 1 | IP3 9PZ | In Progress | Green | 30 weeks start on site to completion | 11/03/2024 | 1360512 | 1232708 | 127804 | 0 | 0 | 0 | 0 | IP3 9PZ | 52.0372 | 1.193 | East of England
YIF - Titans Community Foundation - 2023 |  | 18 | 1 | S60 2AH | In Progress | Green | 28 weeks start on site to completion 20/10-DM - Ready to start on site, subject to Legal DD. | 18/03/2024 | 664974 | 587355 | 77619 | 0 | 0 | 0 | 0 | S60 2AH | 53.424 | -1.3542 | Yorkshire and The Humber
YIF - Onside Preston - 2022 |  | 60 | 1 | PR1 2QA | In Progress | Red | DM 15/1/24 - Program received from Lee Williamson - Anticipated Start Date - 25/3/25 Anticipated PC Date 26/5/25 ENHANCED MONITORING IN PLACE - WEEKLY LEADERSHIP REVIEW - Tender return date 06/10/23 Start on site 18/12/23. Practical completion 24/03 | 25/03/2024 | 8262450 | 6988746 | 1273704 | 789614 | 726922 | 62692 | 0.10401 | PR1 2QA | 53.7589 | -2.6978 | North West
YIF - SUNDERLAND HOME GROWN CIC - 2022 | both the same pc | 12 | 2 | SR5 1SF | Completed | Green | 21 weeks start on site to completion | 19/05/2023 | 490352 | 407352 | 83000 | 490352 | 407352 | 83000 | 1 | SR5 1SF | 54.9238 | -1.3929 | North East
YIF - Plymouth City Council - 2023 (INV-4631) | Poole Farm, Derriford Community park | 16 | 2 | PL6 8NF | Completed | Green | 4 Projects in one Poole Farm Hayloft: 30 weeks, Cabin: 20 weeks Lido Building A: 37 weeks, Building B: 20 weeks | 07/08/2023 | 3463532 | 2789786 | 673746 | 146993.17 | 38262.81 | 108730.36 | 0.013715 | PL6 8NF | 50.4077 | -4.1068 | South West
YIF - Bodies in Motion (Pendle) Ltd - 2023 | Orchid House | 11 | 2 | BB9 5NS | In Progress | Green | DM -30/1/24 - Call arranged with RM who has concerns to discuss timeline/PM & Central support etc. Ridge Review - Start to Completion is 31 weeks. The 90% confidence interval for this estimate is 28 to 33 weeks. Therefore, the applicant’s 43-week ass | 25/01/2024 | 1405920 | 1171600 | 234320 | 149659 | 149659 | 0 | 0.12774 | BB9 5NS | 53.825 | -2.2346 | North West
YIF - East Sussex County Council - 2023 |  | 56 | 2 | BN10 8BL | Completed | Amber | DM 24/1/24 - Heathfield Youth Centre, has forecast completion date of Jan 25 JOFF youth centre has forecast completion date of Dec 24. 56 week build identified on Ridge Report for 1 of the sites. Multi site application | 11/03/2024 | 8019786 | 7623906 | 395880 | 337991 | 337991 | 0 | 0.044333 | BN10 8BL | 50.797 | 0.000376 | South East
YIF - Blackburn with Darwen Borough Council - 2023 |  | 36 | 2 | BB3 3BU | In Progress | Green | DM 25/1/25- Meeting with B&D regarding Planning for Darwin site - Gavin Prescott, Claire Turner, Martin Kelly, Jacques. Planning will be presented at committee on 15th Feb and approval issued on 16th Feb. B&D happy to do follow up reporting on discharging | 08/04/2024 | 4583074 | 4284953 | 298121 | 129533.46 | 129533.46 | 0 | 0.03023 | BB3 3BU | 53.6967 | -2.4662 | North West
YIF - Heart of Hastings CLT Ltd - 2023 | Observer Building | 72 | 2 | TN34 1DT | Completed | Red | 15/1/24 -DM Observer Building Anticipated Completion - April25 19/10- DM - Changed to Amber in line with latest advice from grantee Date of possession: Monday 25th March 2024 (4 weeks mobilisation) Contract Period: 11 months Practical Completion: Fr | 26/04/2024 | 8615656 | 7832043 | 783613 | 2307755 | 1849780 | 384343 | 0.23618 | TN34 1DT | 50.8555 | 0.57628 | South East
YIF - Sheffield City Council - 2023 | All Saints | 13 | 2 | S4 7EP | Completed | Green | 2 Projects - All Saints Youth Club, and Stockbridge Youth Club. Ridge Assessment 25 week build or 6 Months. | 29/04/2024 | 2528218 | 2518218 | 10000 | 0 | 0 | 0 | 0 | S4 7EP | 53.3972 | -1.4544 | Yorkshire and The Humber
YIF - Southmead Development Trust - 2023 |  | 48 | 2 | BS10 5PP | In Progress | Amber | 44 week program (circa11months) RM to seek clarification from the applicant whether the provided dates include both sites, The Greenrooms and The Ranch. | 01/07/2024 | 2579698 | 2191856 | 387842 | 66122 | 23000 | 43122 | 0.010493 | BS10 5PP | 51.499 | -2.6016 | South West
YIF - Portsmouth City Council - 2023 | Chaucer | 30 | 2 | PO1 2DR | In Progress | Green | 2 sites - max 30 weeks start on site to completion | 15/07/2024 | 1393259 | 1153259 | 240000 | 222008 | 222008 | 0 | 0.1925 | PO1 2DR | 50.7972 | -1.0897 | South East
YIF - Knowsley Metropolitan Borough Council - 2023 |  | 32 | 3 | L26 1TT | Completed | Green | DM 30/1/24 Gas report received for two sites Halewood Youth Project & Mosscroft/Karma 3 projects max 26 weeks | 01/02/2024 | 2206570 | 1764570 | 442000 | 135738 | 17897 | 117841 | 0.010142 | L26 1TT | 53.3574 | -2.8377 | North West
YIF - Plymouth City Council - 2023 (INV-4614) |  | 34 | 3 | PL1 5JW | Completed | Green | Dec 21 - still in pre-planning stages. GAS report April. No changes in procurement. Multi-application site for (1) Frederick Street Centre, (2) Efford Youth & Community Centre and (3) Honicknowle Youth & Community Centre. | 06/05/2024 | 2319463 | 1856888 | 462575 | 0 | 0 | 0 | 0 | PL1 5JW | 50.3721 | -4.1529 | South West
YIF - Alt Valley Community Trust Limited - 2022 | Communiversity | 24 | 4 | L11 0BS | In Progress | Green |  | 16/01/2023 | 2612001 | 2462001 | 150000 | 2612001 | 2462001 | 150000 | 1 | L11 0BS | 53.4559 | -2.8986 | North West